## Defects
Sl No | Submitted Date | Description | Description | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | 2026-12-02 | OCR not correctly extracting applicant details from passport image | Sprint 1 | Backend Team | Functional | Enhanced OCR pipeline and tuned Tesseract configs for passport fields | 13/2/2026 | Closed | Applicant details extracted correctly
2 | 18/02/2026 | Missing values causing incorrect visa approval prediction | Sprint 2 | Backend Team | Data/Functional | Added missing‑value imputation and validation checks | 19/02/2026 | Closed | Predictions stabilized
3 | 24/02/2026 | Regression model accuracy not matching validation results | Sprint 2 | ML Team | Algorithmic/Model | Re‑trained regression model with proper validation split | 25/02/2026 | Closed | Accuracy aligned with validation results
4 | 28/02/2026 | Processing time estimator showing negative values | Sprint 2 | ML Team | Logic/ML | Added lower‑bound constraint and re‑scaled outputs | 2026-01-03 | Closed | Negative values eliminated
5 | 2026-04-03 | Visa status result not displayed on UI after prediction | Sprint 3 | Frontend Team | UI/Integration | Fixed UI binding to prediction API and refreshed state handling | 2026-05-03 | Closed | Results now displayed properly
6 | 2026-09-03 | Invalid document upload not handled properly | Sprint 3 | Frontend Team | UI/Validation | Implemented MIME type check and error popup for invalid uploads | 910/3/2026 | Closed | User‑friendly error handling added
7 | 14/03/2026 | API response delay during peak requests | Sprint 3 | Backend Team | Performance | Introduced async processing and caching for peak loads | 15/03/2026 | Closed | Response latency reduced
8 | 17/03/2026 | Dashboard charts not updating after model retraining | Sprint 4 | Frontend Team | Integration/UI | Re‑linked dashboard charts to updated model outputs | 18/03/2026 | Closed | Charts update correctly after retraining
9 | 20/03/2026 | Incorrect visa rejection reason displayed | Sprint 4 | Backend Team | Functional/Logic | Corrected mapping of rejection reasons in backend logic | 21/03/2026 | Closed | Accurate rejection reasons shown
10 | 24/03/2026 | UI alignment and text formatting issues | Sprint 4 | Frontend Team | UI | Adjusted CSS layout and standardized text formatting | 25/03/2026 | Closed | Interface presentation improved